## Summary
Updated by AK on 06/05/2025
Survey response or email update received regarding PLO status for GP practices?
Locality | No | Yes - survey | Yes - email update | Grand Total | % Responded
BOLTON |  | 6 | 43 | 49 | 100%
BURY |  | 16 | 9 | 25 | 100%
HMR | 26 | 10 |  | 36 | 27.78%
MANCHESTER | 50 | 32 |  | 82 | 39.02%
OLDHAM | 27 | 6 |  | 33 | 18.18%
SALFORD | 8 | 8 | 21 | 37 | 78.38%
STOCKPORT | 14 | 10 | 8 | 32 | 56.25%
TAMESIDE | 12 | 4 | 15 | 31 | 61.29%
TRAFFORD | 22 | 3 | 1 | 26 | 15.38%
WIGAN | 38 | 16 | 1 | 55 | 30.91%
Grand Total | 197 | 111 | 98 | 406 | 51.48%
Has your PCN/ practice gone live with patient-led ordering yet?
Locality | No | Yes | Currently implementing | no response | TBC following Chorley Rd implementation | 2025-04-28 | 2025-04-29 | 2025-05-01 | 2025-05-12 | 2025-05-13 | 2025-05-19 | 2025-06-01 | 2025-06-02 | 2025-06-09 | 2025-07-01 | 2025-08-01 | 2025-08-04 | Grand Total
BOLTON | 2 | 3 | 6 |  | 38 | [12 empty] | 49
BURY | 10 | 11 | 4 | [14 empty] | 25
HMR | 5 | 4 | 1 | 26 | [13 empty] | 36
MANCHESTER | 12 | 10 | 10 | 50 | [13 empty] | 82
OLDHAM | 2 | 1 | 3 | 27 | [13 empty] | 33
SALFORD | 6 | 8 |  | 8 |  | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 37
STOCKPORT | 2 | 12 | 4 | 14 | [13 empty] | 32
TAMESIDE | 5 | 12 | 2 | 12 | [13 empty] | 31
TRAFFORD | 3 |  | 1 | 22 | [13 empty] | 26
WIGAN | 15 | 1 | 1 | 38 | [13 empty] | 55
Grand Total | 62 | 62 | 32 | 197 | 38 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 406

## Full list of expected go-live
Locality | PRACTICE NAME | ODS | PCN | Expected go-live month(s) | Survey/ email update received on?
BOLTON | Al Fal Medical Group | P82640 | Bolton Central | Between Dec-24& Feb-25 | 2024-11-01
| Alastair Ross Health Centre | P82018 | Breightmet & Little Lever | TBC following Chorley Rd implementation | 2025-03-01
| Beehive Surgery | P82616 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Bolton Community Practice | Y03079 | Horwich Network | TBC following Chorley Rd implementation | 2025-03-01
| Bolton General Practice | Y02319 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Bolton Medical Centre | Y02790 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Bromley Meadows Surgery | P82643 | Turton | TBC following Chorley Rd implementation | 2025-03-01
| Burnside Surgery | P82025 | HWL Network | TBC following Chorley Rd implementation | 2025-03-01
| Cornerstone surgery | P82627 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Crompton View Surgery | P82607 | Turton | TBC following Chorley Rd implementation | 2025-03-01
| Dalefield Surgery | P82010 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Deane Clinic (Dr Selvarajan) | P82660 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Dr A E Zarrouk & Partner | P82033 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Dr A Kumar & Partner Deane MC | P82030 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Dr C Hallikeri | P82020 | Breightmet & Little Lever | TBC following Chorley Rd implementation | 2025-03-01
| Dr Earnshaw & Partners - Lever Chambers | P82012 | HWL Network | TBC following Chorley Rd implementation | 2025-03-01
| Dr J Leach Edgeworth Medical Centre | P82034 | Turton | TBC following Chorley Rd implementation | 2025-03-01
| Dr James-Authe & Partner | P82634 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Dr M Dakshina-Murthi | P82629 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Dr M Jeyam & Partner The Halliwell Surgery 2 | P82029 | HWL Network | TBC following Chorley Rd implementation | 2025-03-01
| Dr Mirza & Partners - The Pikes Lane Centre | P82002 | Rumworth | Already implemented | 2024-11-01
| Dr N Sidda | P82625 | HWL Network | TBC following Chorley Rd implementation | 2025-03-01
| Dr P A Saul & Partners | P82014 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Dr Rizwan & Partner - The Halliwell Surgery 1 | P82022 | HWL Network | TBC following Chorley Rd implementation | 2025-03-01
| Dr Sidda & Partner | P82633 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Dr Subramanian, Little Lever Health Centre | P82036 | Breightmet & Little Lever | TBC following Chorley Rd implementation | 2025-03-01
| Dr Uddin & Partners The Halliwell Surgery 3 | P82626 | HWL Network | TBC following Chorley Rd implementation | 2025-03-01
| Dr Y Loomba & Partner | P82013 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Fig Tree Medical Practice | P82037 | Farnworth & Kearsley | TBC following Chorley Rd implementation | 2025-03-01
| Garnet Fold Practice | P82009 | Rumworth | TBC following Chorley Rd implementation | 2025-03-01
| Harwood Medical Centre | P82016 | Turton | Between Dec-24& Feb-25 | 2024-11-01
| Heaton Medical Centre | P82031 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Kearsley Medical Centre | P82007 | Farnworth & Kearsley | Already implemented | 2024-11-01
| Kildonan House Group Practice | P82003 | Horwich Network | TBC following Chorley Rd implementation | 2025-03-01
| Mandalay Medical Centre | P82023 | Turton | TBC following Chorley Rd implementation | 2025-03-01
| Orient House Medical Centre | P82624 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Pike View Medical Centre | P82006 | Horwich Network | TBC following Chorley Rd implementation | 2025-03-01
| Shanti Medical Centre | P82609 | Rumworth | TBC following Chorley Rd implementation | 2025-03-01
| Spring View Medical Centre | P82613 | Breightmet & Little Lever | TBC following Chorley Rd implementation | 2025-03-01
| Stable Fold Surgery | P82005 | Westhoughton Network | TBC following Chorley Rd implementation | 2025-03-01
| Stonehill Medical Centre | P82008 | Farnworth & Kearsley | TBC following Chorley Rd implementation | 2025-03-01
| Swan Lane Medical Centre | P82004 | Rumworth | TBC following Chorley Rd implementation | 2025-03-01
| The Dunstan Partnership | P82001 | Breightmet & Little Lever | Already implemented | 2024-11-01
| The Farnworth Family Practice (Dr Barua) | P82652 | Farnworth & Kearsley | TBC following Chorley Rd implementation | 2025-03-01
| The Oaks Family Practice | P82021 | Turton | TBC following Chorley Rd implementation | 2025-03-01
| The Olive Family Practice | Y03366 | Bolton Central | Currently implementing Nov 2024 | 2024-11-01
| Three D Med Centre | Y00186 | Bolton Central | TBC following Chorley Rd implementation | 2025-03-01
| Tonge Fold Health Centre | P82011 | Breightmet & Little Lever | TBC following Chorley Rd implementation | 2025-03-01
| Unsworth Group Practice | P82015 | Westhoughton Network | TBC following Chorley Rd implementation | 2025-03-01
BURY | Blackford House Medical Centre | P83009 | Whitefield District & Community | Not planning to implement | 2025-04-01
| Fairfax Group Practice | P83001 | Prestwich | Currently implementing Feb 2025 | 2025-02-01
| Garden City Medical Centre (SSP Health) | P83620 | Bury | Already implemented | 2025-04-01
| Greylands Medical Centre | P83027 | Prestwich | Currently implementing Jan 2025 | 2025-01-01
| Huntley Mount Medical Centre | P83621 | Bury | Currently implementing Jan 2025 | 2025-04-01
| Knowsley Medical Centre | P83024 | Bury | Not planning to implement | 2025-02-01
| Longfield Medical Practice | P83623 | Prestwich | Between Aug-25& Feb-26 | 2025-02-01
| Mile Lane Surgery | P83612 | Horizon | Between May-25& Aug-25 | 2025-02-01
| Monarch Medical Centre | P83010 | Bury | Already implemented | 2025-02-01
| Peel GP's | P83021 | Horizon | Between Mar-25& May-25 | 2025-04-01
| Radcliffe Medical Practice | P83007 | Bury | Between Aug-25& Feb-26 | 2025-02-01
| Ramsbottom HC | P83006 | Bury | Between Aug-25& Feb-26 | 2025-02-01
| Redbank Group Practice | P83603 | Horizon | Currently implementing Feb 2025 | 2025-02-01
| Ribblesdale HC - Woodcock (Black) | P83015 | Horizon | Currently implementing Jan 2025 | 2025-04-01
| Rock Healthcare | Y02755 | Bury | Between Aug-25& Feb-26 | 2025-02-01
| St Gabriel's Medical Centre | P83025 | Prestwich | Already implemented | 2025-04-01
| The Birches Medical Centre | P83609 | Prestwich | Currently implementing Jan 2025 | 2025-01-01
| The Elms Medical Centre | P83608 | Whitefield District & Community | Between May-25& Aug-25 | 2025-02-01
| Tower Family Healthcare (Tottington) | P83012 | Horizon | Already implemented | 2025-04-01
| Townside Surgery | P83005 | Bury | Currently implementing Feb 2025 | 2025-04-01
| Unsworth Medical Centre | P83011 | Whitefield District & Community | Between Aug-25& Feb-26 | 2025-02-01
| Uplands Medical Centre | P83004 | Whitefield District & Community | Currently implementing Feb 2025 | 2025-02-01
| Walmersley Road Medical Practice | P83611 | Bury | Not planning to implement | 2025-02-01
| Whittaker Lane Medical Centre | P83605 | Prestwich | Already implemented | 2025-02-01
| Woodbank Surgery | P83017 | Horizon | Already implemented | 2025-04-01
HMR | Ashworth Street Surgery | P86006 | Rochdale North | Between Jan-25& Mar-25 | 2024-12-01
| Castleton Health Centre | P86009 | Canalside | Already implemented | 2024-11-01
| Dr Meagher & Partner | P86005 | Rochdale North | Currently implementing Nov 2024 | 2024-11-01
| Dr Swamy & Partner | P86606 | The Bridge | Between Feb-25& May-25 | 2024-11-01
| Durnford Medical Centre | P86019 | Middleton | Currently implementing Nov 2024 | 2024-11-01
| Middleton Surgery | Y02795 | Canalside | Already implemented | 2024-11-01
| Milnrow Village Practice | P86001 | Pennines | Already implemented | 2024-11-01
| The Hive HC, The Surgery Dr Thompson & ptr | Y00726 | Canalside | Between May-25& Nov-25 | 2024-11-01
| The Surgery Dr M Ehsan | P86620 | Middleton | Between Dec-24& Feb-25 | 2024-11-01
| Wellfield Surgery | P86007 | Canalside | Already implemented | 2024-11-01
MANCHESTER | Ailsa Craig Medical Group | P84009 | Ardwick & Longsight | Between Apr-25& Oct-25 | 2024-10-01
| Al-Shifa Medical Centre | P84665 | Withington & Fallowfield | Currently implementing Oct 2024 | 2024-10-01
| Ashville Surgery | P84038 | West Central Manchester | Between Dec-24& Feb-25 | 2024-11-01
| Barlow Medical Centre | P84034 | Didsbury Chorlton Park & Burnage | Not planning to implement | 2024-11-01
| Benchill Medical Practice | P84029 | Wythenshawe | Already implemented | 2024-10-01
| Bodey Medical Centre | P84035 | Withington & Fallowfield | Already implemented | 2024-11-01
| Borchardt Medical Centre | P84010 | Withington & Fallowfield | Already implemented | 2024-10-01
| Bowland Medical Practice | P84024 | Wythenshawe | Already implemented | 2024-10-01
| Brooklands Medical Practice | P84061 | Northenden & Brooklands (Wythenshawe) | Currently implementing Nov 2024 | 2024-11-01
| Collegiate Medical Centre | P84030 | Cheetham Hill & Crumpsall | Already implemented | 2024-10-01
| Dam Head Medical Centre | P84690 | H-Blackley Harpurhey & Charlestown | Already implemented | 2024-10-01
| David Medical Centre | P84066 | Didsbury Chorlton Park & Burnage | Between Jan-25& Apr-25 | 2024-10-01
| Didsbury Medical Centre - Dr Whittaker | P84678 | Didsbury Chorlton Park & Burnage | Between May-25& Nov-25 | 2024-11-01
| Kingsway Medical Practice | P84022 | Didsbury Chorlton Park & Burnage | Between Jan-25& Mar-25 | 2024-12-01
| Levenshulme Health Centre | P84016 | Gorton & Levenshulme | Between Jan-25& Apr-25 | 2024-10-01
| Mount Road Surgery | P84050 | Gorton & Levenshulme | Currently implementing Oct 2024 | 2024-10-01
| New Bank Health Centre | Y02960 | Better Health MCR PCN | Between Jan-25& Apr-25 | 2024-10-01
| New Islington Medical Practice | P84064 | City Centre & Ancoats | Currently implementing Nov 2024 | 2024-11-01
| Northenden Group Practice | P84012 | Northenden & Brooklands (Wythenshawe) | Currently implementing Nov 2024 | 2024-11-01
| Park View Medical Centre | P84645 | Cheetham Hill & Crumpsall | Currently implementing Nov 2024 | 2024-11-01
| St Georges Medical Centre | P84025 | Miles Platting, Newton Heath & Moston | Currently implementing Nov 2024 | 2024-11-01
| Surrey Lodge Group Practice | P84023 | Ardwick & Longsight | Already implemented | 2024-10-01
| The Hawthorn Medical Centre | Y02890 | Gorton & Levenshulme | Already implemented | 2024-10-01
| The Robert Darbishire Practice Ltd. | P84072 | Better Health MCR PCN | Between Jan-25& Apr-25 | 2024-10-01
| The Singh Medical Practice (Harpurhey Health Centre) | P84065 | H-Blackley Harpurhey & Charlestown | Already implemented | 2024-10-01
| The Whitswood Practice | P84635 | Better Health MCR PCN | Between Jan-25& Apr-25 | 2024-10-01
| Tregenna Group Practice | P84048 | Wythenshawe | Already implemented | 2024-11-01
| Urban Village Medical Practice | P84673 | City Centre & Ancoats | Currently implementing Oct 2024 | 2024-10-01
| Wellfield Medical Centre | P84074 | Cheetham Hill & Crumpsall | Between Apr-25& Oct-25 | 2024-10-01
| Whitley Road Medical Centre | P84054 | Miles Platting, Newton Heath & Moston | Currently implementing Nov 2024 | 2024-11-01
| Wilbraham Surgery | P84071 | West Central Manchester | Currently implementing Oct 2024 | 2024-10-01
| Woodlands Medical Practice | P84672 | Northenden & Brooklands (Wythenshawe) | Between Dec-24& Feb-25 | 2024-11-01
OLDHAM | CH Medical Practice | P85011 | Milltown Alliance | Currently implementing Nov 2024 | 2024-11-01
| Glodwick Medical practice | P85622 | Oldham Central | Between Jan-25& Apr-25 | 2024-10-01
| John Street Medical Practice | Y02827 | Oldham Central | Currently implementing Nov 2024 | 2024-11-01
| Kapur Family Care | P85615 | Milltown Alliance | Not planning to implement | 2024-11-01
| Oak Gables Partnership | P85017 | Oldham North | Currently implementing Oct 2024 | 2024-10-01
| Royton Medical Centre | P85019 | Oldham North | Already implemented | 2024-10-01
SALFORD | Blackfriars Medical Practice | Y02622 | Broughton Health Alliance | Already implemented | 2024-10-01
| Chapel Medical Centre | P87649 | Eccles & Irlam | Already implemented | 2025-04-01
| Cherry Medical Practice | P87630 | Walkden & Little Hulton | Already implemented | 2024-11-01
| Clarendon Surgery | P87634 | Salford South East PCN | 2025-06-01 | 2025-04-01
| Cornerstone Medical Practice | P87639 | Salford South East PCN | 2025-05-19 | 2025-04-01
| Dearden Avenue Medical Practice | P87625 | Walkden & Little Hulton | 2025-05-01 | 2025-04-01
| Ellenbrook Medical Practice | P87624 | Walkden & Little Hulton | Between Feb-25& May-25 | 2024-11-01
| Langworthy Medical Practice | P87027 | Salford South East PCN | Already implemented | 2025-04-01
| Lower Broughton 3 (Dr Jeet) | P87654 | Broughton Health Alliance | 2025-06-01 | 2025-04-01
| Manchester Road East Medical Practice | P87661 | Walkden & Little Hulton | 2025-05-13 | 2025-04-01
| Mocha Parade Medical Practice | P87022 | Broughton Health Alliance | Between May-25& Nov-25 | 2024-11-01
| Monton Medical Centre | P87620 | Eccles & Irlam | 2025-06-02 | 2025-04-01
| Newbury Green Medical Practice | P87026 | Broughton Health Alliance | no response | 2024-10-01
| Orchard Medical Practice | P87627 | Walkden & Little Hulton | 2025-05-12 | 2025-04-01
| Ordsall Health Surgery | P87035 | Salford South East PCN | Between Dec-24& Feb-25 | 2024-11-01
| Orient Road Medical Practice | P87032 | Salford South East PCN | 2025-07-01 | 2025-04-01
| Pendleton Medical Centre | P87015 | Salford South East PCN | 2025-04-01 | 2025-04-01
| Salford Care Centres Irlam Clinic | P87657 | Eccles & Irlam | 2025-05-19 | 2025-04-01
| Salford Medical Centre | P87004 | Salford South East PCN | Already implemented | 2025-04-01
| Salford Primary Care Together | Y00445 | Eccles & Irlam | 2025-04-28 | 2025-04-01
| Silverdale Medical Practice | P87019 | Swinton | 2025-04-01 | 2025-04-01
| Springfield Medical Centre | P87024 | Eccles & Irlam | 2025-08-01 | 2025-04-01
| St. Andrews Medical Practice 2 | P87020 | Eccles & Irlam | 2025-04-29 | 2025-04-01
| The Gill Medical Centre | P87028 | Walkden & Little Hulton | 2025-08-04 | 2025-04-01
| The Height General Practice | Y02767 | Salford South East PCN | Already implemented | 2025-04-01
| The Lakes Medical Practice | P87025 | Swinton | Between Dec-24& Feb-25 | 2024-11-01
| The Limes Medical Practice | P87017 | Walkden & Little Hulton | Between Jun-25& Dec-25 | 2024-12-01
| The Sides Medical Centre | P87016 | Swinton | 2025-06-09 | 2025-04-01
| The Willows Medical Centre | P87658 | Salford South East PCN | 2025-05-01 | 2025-04-01
STOCKPORT | Adshall Road Medical Practice | P88014 | Victoria | Already implemented | 2025-04-01
| Alvanley Family Practice | P88019 | Tame Valley | Between Jun-25& Sep-25 | 2025-03-01
| Archwood Medical Practice | P88625 | Stockport East & South PCN | Currently implementing Nov 2024 | 2024-11-01
| Bracondale Medical Centre | P88031 | Victoria | Already implemented | 2025-04-01
| Bramhall Health Centre (Dr Pozzoni & Ptners) | P88015 | Bramhall & Cheadle Hulme | Already implemented | 2024-11-01
| Caritas General Practice | P88013 | Victoria | Already implemented | 2025-04-01
| Cheadle Hulme HC (Dr Seabrook Ptners) | P88007 | Bramhall & Cheadle Hulme | Currently implementing Nov 2024 | 2024-11-01
| Cheadle Medical Practice (Dr Mehta & Ptners) | P88020 | Cheadle Network | 1905-07-16 | 2025-04-01
| Dr Gilman & Parnters Brinnington Health Centre | P88043 | Tame Valley | Already implemented | 2024-12-01
| Family Surgery, Reddish (Dr Dickie & Partners) | P88005 | Tame Valley | Currently implementing Dec 2024 | 2024-12-01
| Finley Lane Surgery | P88042 | Cheadle Network | Already implemented | 2025-04-01
| Gatley Medical Centre (Dr Davison & Ptners) | P88024 | Cheadle Network | Already implemented | 2025-04-01
| Heald Green HC 2 (Dr Morris & Ptners) | P88023 | Cheadle Network | 1905-07-16 | 2025-04-01
| Hulme Hall Medical Group | P88025 | Bramhall & Cheadle Hulme | Already implemented | 2025-03-01
| Marple Bridge Surgery | P88002 | Stockport East & South PCN | Already implemented | 2024-11-01
| Park View Group Practice (Dr Hussain & Partners) | P88018 | Tame Valley | Currently implementing Dec 2024 | 2024-12-01
| Stockport Medical Group | P88632 | Victoria | Already implemented | 2025-04-01
| Vernon Park Surgery - Dr Chatterjee | P88615 | Tame Valley | Currently implementing Dec 2024 | 2024-12-01
TAMESIDE | Ashton GP Service | Y02586 | Ashton | no info | 2024-12-01
| Ashton medical Group | P89008 | Ashton | no info | 2024-12-01
| Clarendon Medical Centre | P89012 | Hyde | Already implemented | 2024-12-01
| Dukinfield Medical Centre | P89021 | Hyde | Already implemented | 2024-11-01
| Gordon Street Medical Centre | P89011 | Ashton | no info | 2024-12-01
| Grosvenor Medical Centre | P89026 | Stalybridge | Already implemented | 2024-12-01
| Hattersley Group Practice | P89013 | Hyde | Already implemented | 2024-12-01
| HT Practice | P89020 | Ashton | Already implemented | 2024-12-01
| King Street Medical Centre | P89022 | Stalybridge | Already implemented | 2024-12-01
| Lockside Medical Centre | P89005 | Stalybridge | Currently implementing Nov 2024 | 2024-11-01
| Medlock Vale Medical Practice | P89010 | Denton | Already implemented | 2024-12-01
| Millbrook Medical Practice | Y02936 | Stalybridge | Already implemented | 2024-12-01
| Mossley Medical Practice | P89612 | Stalybridge | Already implemented | 2024-12-01
| St. Andrews House | P89023 | Stalybridge | no info | 2024-12-01
| Stamford House | P89609 | Ashton | no info | 2024-12-01
| Staveleigh Medical Centre | P89007 | Stalybridge | Currently implementing Nov 2024 | 2024-11-01
| The Smithy Surgery | P89602 | Hyde | Already implemented | 2024-12-01
| Town Hall Surgery | P89025 | Stalybridge | Already implemented | 2024-12-01
| West End Medical Centre | P89030 | Ashton | Already implemented | 2024-12-01
TRAFFORD | Barrington Medical Centre | P91603 | South Trafford | Not planning to implement | 2024-11-01
| Limelight Health Wellbeing Hub | P91020 | North Trafford | Not planning to implement | 2024-11-01
| St Johns Medical Centre | P91604 | Altrincham Healthcare Alliance | 2025-07-01 | 2025-04-01
| The Delamere Medical Practice | P91018 | North Trafford | Currently implementing Nov 2024 | 2024-11-01
WIGAN | Aspull Surgery | P92015 | North Wigan | Not planning to implement | 2025-02-01
| Boothstown Medical Centre (Anderson & Partner) | P92605 | TABA Wigan | Between Aug-25& Feb-26 | 2025-02-01
| Bryn Cross Surgery | P92034 | SWAN Network Wigan | no info | 2025-02-01
| Bryn Street Surgery | Y02378 | LiGA Wigan | Not planning to implement | 2025-02-01
| Dr Shahbazi Family Medical Practice | P92639 | LiGA Wigan | Not planning to implement | 2025-02-01
| Dr Vardhan's Surgery | P92646 | TABA Wigan | Not planning to implement | 2025-02-01
| Drs D’Arifat, Elislam, Wan & Shaikh (Newtown Medical Practice) | P92021 | Wigan Central | Between Aug-25& Feb-26 | 2025-02-01
| Ellis & Partner Mesnes View Surgery | P92634 | Wigan Central | Between Mar-25& May-25 | 2025-02-01
| Foxleigh Family Surgery | P92602 | Leigh | Between Aug-25& Feb-26 | 2025-02-01
| Lower Ince Surgery – Dr Wahie | P92620 | Hindley | Between Aug-25& Feb-26 | 2025-02-01
| Marsh Green Medical Practice | Y02885 | Wigan Central | Between Aug-25& Feb-26 | 2025-02-01
| Marus Bridge Practice | P92642 | SWAN Network Wigan | Currently implementing Feb 2025 | 2025-02-01
| Pemberton Surgery | P92019 | Wigan Central | Not planning to implement | 2025-02-01
| Pennygate Medical Centre | P92016 | Hindley | Not planning to implement | 2025-02-01
| Saxena Winstanley Medical Centre | P92038 | SWAN Network Wigan | 2025-07-01 | 2025-04-01
| Shevington Surgery | P92017 | North Wigan | Already implemented | 2025-02-01
| The Dicconson Group Practice (Mughal and Partners ) | P92003 | Wigan Central | Between Mar-25& May-25 | 2025-02-01

## Implemented
Locality | PRACTICE NAME | ODS | PCN | Expected go-live month(s) | Survey/ email update received on?
Locality | PRACTICE NAME | ODS | PCN | Expected go-live month(s) | Survey/ email update received on?
BOLTON | Dr Mirza & Partners - The Pikes Lane Centre | P82002 | Rumworth | Already implemented | 2024-11-01
| Kearsley Medical Centre | P82007 | Farnworth & Kearsley | Already implemented | 2024-11-01
| The Dunstan Partnership | P82001 | Breightmet & Little Lever | Already implemented | 2024-11-01
BURY | Blackford House Medical Centre | P83009 | Whitefield District & Community | Not planning to implement | 2025-04-01
| Garden City Medical Centre (SSP Health) | P83620 | Bury | Already implemented | 2025-04-01
| Huntley Mount Medical Centre | P83621 | Bury | Currently implementing Jan 2025 | 2025-04-01
| Monarch Medical Centre | P83010 | Bury | Already implemented | 2025-02-01
| Peel GP's | P83021 | Horizon | Between Mar-25& May-25 | 2025-04-01
| Ribblesdale HC - Woodcock (Black) | P83015 | Horizon | Currently implementing Jan 2025 | 2025-04-01
| St Gabriel's Medical Centre | P83025 | Prestwich | Already implemented | 2025-04-01
| Tower Family Healthcare (Tottington) | P83012 | Horizon | Already implemented | 2025-04-01
| Townside Surgery | P83005 | Bury | Currently implementing Feb 2025 | 2025-04-01
| Whittaker Lane Medical Centre | P83605 | Prestwich | Already implemented | 2025-02-01
| Woodbank Surgery | P83017 | Horizon | Already implemented | 2025-04-01
HMR | Castleton Health Centre | P86009 | Canalside | Already implemented | 2024-11-01
| Middleton Surgery | Y02795 | Canalside | Already implemented | 2024-11-01
| Milnrow Village Practice | P86001 | Pennines | Already implemented | 2024-11-01
| Wellfield Surgery | P86007 | Canalside | Already implemented | 2024-11-01
MANCHESTER | Benchill Medical Practice | P84029 | Wythenshawe | Already implemented | 2024-10-01
| Bodey Medical Centre | P84035 | Withington & Fallowfield | Already implemented | 2024-11-01
| Borchardt Medical Centre | P84010 | Withington & Fallowfield | Already implemented | 2024-10-01
| Bowland Medical Practice | P84024 | Wythenshawe | Already implemented | 2024-10-01
| Collegiate Medical Centre | P84030 | Cheetham Hill & Crumpsall | Already implemented | 2024-10-01
| Dam Head Medical Centre | P84690 | H-Blackley Harpurhey & Charlestown | Already implemented | 2024-10-01
| Surrey Lodge Group Practice | P84023 | Ardwick & Longsight | Already implemented | 2024-10-01
| The Hawthorn Medical Centre | Y02890 | Gorton & Levenshulme | Already implemented | 2024-10-01
| The Singh Medical Practice (Harpurhey Health Centre) | P84065 | H-Blackley Harpurhey & Charlestown | Already implemented | 2024-10-01
| Tregenna Group Practice | P84048 | Wythenshawe | Already implemented | 2024-11-01
OLDHAM | Royton Medical Centre | P85019 | Oldham North | Already implemented | 2024-10-01
SALFORD | Blackfriars Medical Practice | Y02622 | Broughton Health Alliance | Already implemented | 2024-10-01
| Chapel Medical Centre | P87649 | Eccles & Irlam | Already implemented | 2025-04-01
| Cherry Medical Practice | P87630 | Walkden & Little Hulton | Already implemented | 2024-11-01
| Langworthy Medical Practice | P87027 | Salford South East PCN | Already implemented | 2025-04-01
| Pendleton Medical Centre | P87015 | Salford South East PCN | 45748 | 2025-04-01
| Salford Medical Centre | P87004 | Salford South East PCN | Already implemented | 2025-04-01
| Silverdale Medical Practice | P87019 | Swinton | 45748 | 2025-04-01
| The Height General Practice | Y02767 | Salford South East PCN | Already implemented | 2025-04-01
STOCKPORT | Adshall Road Medical Practice | P88014 | Victoria | Already implemented | 2025-04-01
| Bracondale Medical Centre | P88031 | Victoria | Already implemented | 2025-04-01
| Bramhall Health Centre (Dr Pozzoni & Ptners) | P88015 | Bramhall & Cheadle Hulme | Already implemented | 2024-11-01
| Caritas General Practice | P88013 | Victoria | Already implemented | 2025-04-01
| Cheadle Medical Practice (Dr Mehta & Ptners) | P88020 | Cheadle Network | 2024 | 2025-04-01
| Dr Gilman & Parnters Brinnington Health Centre | P88043 | Tame Valley | Already implemented | 2024-12-01
| Finley Lane Surgery | P88042 | Cheadle Network | Already implemented | 2025-04-01
| Gatley Medical Centre (Dr Davison & Ptners) | P88024 | Cheadle Network | Already implemented | 2025-04-01
| Heald Green HC 2 (Dr Morris & Ptners) | P88023 | Cheadle Network | 2024 | 2025-04-01
| Hulme Hall Medical Group | P88025 | Bramhall & Cheadle Hulme | Already implemented | 2025-03-01
| Marple Bridge Surgery | P88002 | Stockport East & South PCN | Already implemented | 2024-11-01
| Stockport Medical Group | P88632 | Victoria | Already implemented | 2025-04-01
TAMESIDE | Clarendon Medical Centre | P89012 | Hyde | Already implemented | 2024-12-01
| Dukinfield Medical Centre | P89021 | Hyde | Already implemented | 2024-11-01
| Grosvenor Medical Centre | P89026 | Stalybridge | Already implemented | 2024-12-01
| Hattersley Group Practice | P89013 | Hyde | Already implemented | 2024-12-01
| HT Practice | P89020 | Ashton | Already implemented | 2024-12-01
| King Street Medical Centre | P89022 | Stalybridge | Already implemented | 2024-12-01
| Medlock Vale Medical Practice | P89010 | Denton | Already implemented | 2024-12-01
| Millbrook Medical Practice | Y02936 | Stalybridge | Already implemented | 2024-12-01
| Mossley Medical Practice | P89612 | Stalybridge | Already implemented | 2024-12-01
| The Smithy Surgery | P89602 | Hyde | Already implemented | 2024-12-01
| Town Hall Surgery | P89025 | Stalybridge | Already implemented | 2024-12-01
| West End Medical Centre | P89030 | Ashton | Already implemented | 2024-12-01
WIGAN | Shevington Surgery | P92017 | North Wigan | Already implemented | 2025-02-01

## Currently Implementing
Locality | PRACTICE NAME | ODS | PCN | Expected go-live month(s) | Survey/ email update received on?
Locality | PRACTICE NAME | ODS | PCN | Expected go-live month(s) | Survey/ email update received on?
BOLTON | Cornerstone surgery | P82627 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Dalefield Surgery | P82010 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Dr James-Authe & Partner | P82634 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Dr P A Saul & Partners | P82014 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| Heaton Medical Centre | P82031 | Chorley Roads Network | 2025-05-01 | 2025-03-01
| The Olive Family Practice | Y03366 | Bolton Central | Currently implementing Nov 2024 | 2024-11-01
BURY | Fairfax Group Practice | P83001 | Prestwich | Currently implementing Feb 2025 | 2025-02-01
| Greylands Medical Centre | P83027 | Prestwich | Currently implementing Jan 2025 | 2025-01-01
| Redbank Group Practice | P83603 | Horizon | Currently implementing Feb 2025 | 2025-02-01
| The Birches Medical Centre | P83609 | Prestwich | Currently implementing Jan 2025 | 2025-01-01
HMR | Durnford Medical Centre | P86019 | Middleton | Currently implementing Nov 2024 | 2024-11-01
MANCHESTER | Al-Shifa Medical Centre | P84665 | Withington & Fallowfield | Currently implementing Oct 2024 | 2024-10-01
| Brooklands Medical Practice | P84061 | Northenden & Brooklands (Wythenshawe) | Currently implementing Nov 2024 | 2024-11-01
| Mount Road Surgery | P84050 | Gorton & Levenshulme | Currently implementing Oct 2024 | 2024-10-01
| New Islington Medical Practice | P84064 | City Centre & Ancoats | Currently implementing Nov 2024 | 2024-11-01
| Northenden Group Practice | P84012 | Northenden & Brooklands (Wythenshawe) | Currently implementing Nov 2024 | 2024-11-01
| Park View Medical Centre | P84645 | Cheetham Hill & Crumpsall | Currently implementing Nov 2024 | 2024-11-01
| St Georges Medical Centre | P84025 | Miles Platting, Newton Heath & Moston | Currently implementing Nov 2024 | 2024-11-01
| Urban Village Medical Practice | P84673 | City Centre & Ancoats | Currently implementing Oct 2024 | 2024-10-01
| Whitley Road Medical Centre | P84054 | Miles Platting, Newton Heath & Moston | Currently implementing Nov 2024 | 2024-11-01
| Wilbraham Surgery | P84071 | West Central Manchester | Currently implementing Oct 2024 | 2024-10-01
OLDHAM | CH Medical Practice | P85011 | Milltown Alliance | Currently implementing Nov 2024 | 2024-11-01
| John Street Medical Practice | Y02827 | Oldham Central | Currently implementing Nov 2024 | 2024-11-01
| Oak Gables Partnership | P85017 | Oldham North | Currently implementing Oct 2024 | 2024-10-01
STOCKPORT | Archwood Medical Practice | P88625 | Stockport East & South PCN | Currently implementing Nov 2024 | 2024-11-01
| Cheadle Hulme HC (Dr Seabrook Ptners) | P88007 | Bramhall & Cheadle Hulme | Currently implementing Nov 2024 | 2024-11-01
| Family Surgery, Reddish (Dr Dickie & Partners) | P88005 | Tame Valley | Currently implementing Dec 2024 | 2024-12-01
| Vernon Park Surgery - Dr Chatterjee | P88615 | Tame Valley | Currently implementing Dec 2024 | 2024-12-01
TAMESIDE | Lockside Medical Centre | P89005 | Stalybridge | Currently implementing Nov 2024 | 2024-11-01
| Staveleigh Medical Centre | P89007 | Stalybridge | Currently implementing Nov 2024 | 2024-11-01
TRAFFORD | The Delamere Medical Practice | P91018 | North Trafford | Currently implementing Nov 2024 | 2024-11-01
WIGAN | Marus Bridge Practice | P92642 | SWAN Network Wigan | Currently implementing Feb 2025 | 2025-02-01

## Planning to implement
Locality | Locality | PRACTICE NAME | ODS | PCN | If no, is your PCN/ practice planning to go live in coming months? | Expected go-live month(s) | Survey/ email update received on?
BOLTON | BOLTON | Al Fal Medical Group | P82640 | Bolton Central | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
|  | Harwood Medical Centre | P82016 | Turton | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
BURY | BURY | Longfield Medical Practice | P83623 | Prestwich | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Mile Lane Surgery | P83612 | Horizon | In 3 to 6 months | Between May-25& Aug-25 | 2025-02-01
|  | Radcliffe Medical Practice | P83007 | Bury | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Ramsbottom HC | P83006 | Bury | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Rock Healthcare | Y02755 | Bury | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | The Elms Medical Centre | P83608 | Whitefield District & Community | In 3 to 6 months | Between May-25& Aug-25 | 2025-02-01
|  | Unsworth Medical Centre | P83011 | Whitefield District & Community | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Uplands Medical Centre | P83004 | Whitefield District & Community | Currently implementing | Currently implementing Feb 2025 | 2025-02-01
| HMR | Ashworth Street Surgery | P86006 | Rochdale North | In 1 to 3 months | Between Jan-25& Mar-25 | 2024-12-01
HMR |  | Dr Meagher & Partner | P86005 | Rochdale North | Currently implementing | Currently implementing Nov 2024 | 2024-11-01
|  | Dr Swamy & Partner | P86606 | The Bridge | In 3 to 6 months | Between Feb-25& May-25 | 2024-11-01
|  | The Hive HC, The Surgery Dr Thompson & ptr | Y00726 | Canalside | In 6 to 12 months | Between May-25& Nov-25 | 2024-11-01
|  | The Surgery Dr M Ehsan | P86620 | Middleton | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
| MANCHESTER | Ailsa Craig Medical Group | P84009 | Ardwick & Longsight | In 6 to 12 months | Between Apr-25& Oct-25 | 2024-10-01
MANCHESTER |  | Ashville Surgery | P84038 | West Central Manchester | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
|  | David Medical Centre | P84066 | Didsbury Chorlton Park & Burnage | In 3 to 6 months | Between Jan-25& Apr-25 | 2024-10-01
|  | Didsbury Medical Centre - Dr Whittaker | P84678 | Didsbury Chorlton Park & Burnage | In 6 to 12 months | Between May-25& Nov-25 | 2024-11-01
|  | Kingsway Medical Practice | P84022 | Didsbury Chorlton Park & Burnage | In 1 to 3 months | Between Jan-25& Mar-25 | 2024-12-01
|  | Levenshulme Health Centre | P84016 | Gorton & Levenshulme | In 3 to 6 months | Between Jan-25& Apr-25 | 2024-10-01
|  | New Bank Health Centre | Y02960 | Better Health MCR PCN | In 3 to 6 months | Between Jan-25& Apr-25 | 2024-10-01
|  | The Robert Darbishire Practice Ltd. | P84072 | Better Health MCR PCN | In 3 to 6 months | Between Jan-25& Apr-25 | 2024-10-01
|  | The Whitswood Practice | P84635 | Better Health MCR PCN | In 3 to 6 months | Between Jan-25& Apr-25 | 2024-10-01
|  | Wellfield Medical Centre | P84074 | Cheetham Hill & Crumpsall | In 6 to 12 months | Between Apr-25& Oct-25 | 2024-10-01
|  | Woodlands Medical Practice | P84672 | Northenden & Brooklands (Wythenshawe) | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
| OLDHAM | Glodwick Medical practice | P85622 | Oldham Central | In 3 to 6 months | Between Jan-25& Apr-25 | 2024-10-01
OLDHAM | SALFORD | Ellenbrook Medical Practice | P87624 | Walkden & Little Hulton | In 3 to 6 months | Between Feb-25& May-25 | 2024-11-01
SALFORD |  | Mocha Parade Medical Practice | P87022 | Broughton Health Alliance | In 6 to 12 months | Between May-25& Nov-25 | 2024-11-01
|  | Ordsall Health Surgery | P87035 | Salford South East PCN | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
|  | The Lakes Medical Practice | P87025 | Swinton | In 1 to 3 months | Between Dec-24& Feb-25 | 2024-11-01
|  | The Limes Medical Practice | P87017 | Walkden & Little Hulton | In 6 to 12 months | Between Jun-25& Dec-25 | 2024-12-01
| STOCKPORT | Alvanley Family Practice | P88019 | Tame Valley | In 3 to 6 months | Between Jun-25& Sep-25 | 2025-03-01
|  | Park View Group Practice (Dr Hussain & Partners) | P88018 | Tame Valley | Currently implementing | Currently implementing Dec 2024 | 2024-12-01
| TAMESIDE | Ashton GP Service | Y02586 | Ashton | email update | no info | 2024-12-01
|  | Ashton medical Group | P89008 | Ashton | email update | no info | 2024-12-01
|  | Gordon Street Medical Centre | P89011 | Ashton | email update | no info | 2024-12-01
|  | St. Andrews House | P89023 | Stalybridge | email update | no info | 2024-12-01
|  | Stamford House | P89609 | Ashton | email update | no info | 2024-12-01
| TRAFFORD | St Johns Medical Centre | P91604 | Altrincham Healthcare Alliance | email update | 2025-07-01 | 2025-04-01
| WIGAN | Boothstown Medical Centre (Anderson & Partner) | P92605 | TABA Wigan | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Drs D’Arifat, Elislam, Wan & Shaikh (Newtown Medical Practice) | P92021 | Wigan Central | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
STOCKPORT |  | Ellis & Partner Mesnes View Surgery | P92634 | Wigan Central | In 1 to 3 months | Between Mar-25& May-25 | 2025-02-01
|  | Foxleigh Family Surgery | P92602 | Leigh | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Lower Ince Surgery – Dr Wahie | P92620 | Hindley | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
|  | Marsh Green Medical Practice | Y02885 | Wigan Central | In 6 to 12 months | Between Aug-25& Feb-26 | 2025-02-01
TAMESIDE |  | The Dicconson Group Practice (Mughal and Partners ) | P92003 | Wigan Central | In 1 to 3 months | Between Mar-25& May-25 | 2025-02-01
TRAFFORD
WIGAN

## Not Planning to Implement
Locality | PRACTICE NAME | ODS | PCN | If no, is your PCN/ practice planning to go live in coming months? | Survey/ email update received on?
BURY | Knowsley Medical Centre | P83024 | Bury | Not planning to implement | 2025-02-01
| Walmersley Road Medical Practice | P83611 | Bury | Not planning to implement | 2025-02-01
MANCHESTER | Barlow Medical Centre | P84034 | Didsbury Chorlton Park & Burnage | Not planning to implement | 2024-11-01
OLDHAM | Kapur Family Care | P85615 | Milltown Alliance | Not planning to implement | 2024-11-01
SALFORD | Newbury Green Medical Practice | P87026 | Broughton Health Alliance | Not planning to implement | 2024-10-01
TRAFFORD | Barrington Medical Centre | P91603 | South Trafford | Not planning to implement | 2024-11-01
| Limelight Health Wellbeing Hub | P91020 | North Trafford | Not planning to implement | 2024-11-01
WIGAN | Aspull Surgery | P92015 | North Wigan | Not planning to implement | 2025-02-01
| Bryn Street Surgery | Y02378 | LiGA Wigan | Not planning to implement | 2025-02-01
| Dr Shahbazi Family Medical Practice | P92639 | LiGA Wigan | Not planning to implement | 2025-02-01
| Dr Vardhan's Surgery | P92646 | TABA Wigan | Not planning to implement | 2025-02-01
| Pemberton Surgery | P92019 | Wigan Central | Not planning to implement | 2025-02-01
| Pennygate Medical Centre | P92016 | Hindley | Not planning to implement | 2025-02-01